## Sheet2
Phase / Task ID | Task Description | Start Week | End Week | Duration (Weeks) | TASK | month 1 | month 2 | month 3 | month 4 | month 5 | month 6 | month 7 | month 8 | month 9 | month 10 | month 11 | month 12 | FEB | MAR | APR
PHASE 1 | Metadata & SDK Integration |  |  |  | 1
T1 | Semantic Mapping to Ocean DDO Standards | 1 | 4 | 4 | 2
T2 | Client-Side ocean.js Wrapper Setup | 4 | 8 | 5 | 3
T3 | Provider URL Encryption Setup | 7 | 12 | 6 | 4
PHASE 2 | On-Chain Asset Creation |  |  |  | 5
T4 | Automated Data NFT Factory Deployment | 13 | 18 | 6 | 6
T5 | Datatoken Sub-Access Generation | 16 | 21 | 6 | 7
T6 | Testnet Price Anchor Configuration | 20 | 24 | 5 | 8
PHASE 3 | Compute-to-Data Sandbox |  |  |  | 9
T7 | Isolated Provider Compute Setup | 25 | 30 | 6
T8 | Algorithmic Docker Container Screening | 28 | 36 | 9
PHASE 4 | Mainnet & UI Launch
T9 | Production dApp Dashboard Integration | 35 | 48 | 14